## Rollout
Site ID | Site | Stage | Wave | Owner | Carrier | Circuit ID | FOC | Install date | Mgmt IP | LAN | VLAN | Uplink | Edge serial | Notes
0012 | Store 12 Duluth | Accepted | 1 | M. Reyes | Northline Fiber | NLF/DIA/004512 | 2026-09-08 | 2026-09-15 | 10.20.12.1 | 10.20.12.0/24 | 12 | Gi1/0/48 | FGL2231A0KZ | Example row. Delete these three when you start.
0027 | Store 27 Superior | Scheduled | 1 | M. Reyes | Northline Fiber | NLF/DIA/004538 | 2026-11-12 | 2026-11-10 | 10.20.27.1 | 10.20.27.0/24 | 27 | Gi1/0/48 |  | FOC lands after the install date, so the FOC cell is amber.
0103 | Store 103 Hibbing | Ordered | 2 | J. Park | Iron Range Telecom | IRT-778120-ETH |  | 2026-12-01 | 10.21.3.1 | 10.21.3.0/24 | 103 | Gi1/0/48 |  | Waiting on FOC from the carrier.

## Tasks
Task | Status | Owner | Vendor | Due | Phase | Notes
Confirm spare PSU stock for wave 2 | In progress | J. Park | Iron Range Telecom | 2026-10-30 | Wave 2 | Example row.
Update as-built for Store 12 | Not started | M. Reyes |  | 2026-09-18 | Wave 1 | Past due and not done, so the date is red.
Order staging switches | Done | M. Reyes | Northline Fiber | 2026-09-01 | Wave 1

## Summary
Sites by stage | Tasks by status
Planned | Not started
Survey | In progress
Ordered | Blocked
Ready | Done
Scheduled | Overdue
Installed
Cut over
Accepted
Total sites
Install date passed, not installed
FOC after install date

## Read me
Project tracker template
From kodura.io/blog/project-tracker-excel. Free to use and change.
The sheets
Rollout: one row per site, moving through eight stages from Planned to Accepted.
Tasks: everything that isn't a site. Owner, vendor, due date, status.
Summary: counts for a weekly status update. It's all formulas, so don't type in it.
How to use it
Delete the example rows, then type or paste below the headers. The tables grow as you add rows.
Stage and Status are dropdowns. Summary counts them by exact name, so pick from the list.
Site ID, Circuit ID, Mgmt IP, LAN, Uplink and Edge serial are formatted as text before you type.
That keeps leading zeros (0012 stays 0012) and stops long serials turning into 1.23E+15.
When pasting from another workbook, use Paste Special > Values so the cells keep that text format.
What the colours mean
Red install or due date: the date has passed and the site isn't installed, or the task isn't done.
Amber FOC: the carrier's committed date is after your install date. Move one of them.
Grey row: accepted or done.